## RA Sprints
Sprints Draft Plan
Sprint-1
Data Modeling
User's, Institution, Projects
Desigining
HomePage, Login, Signup
Prelogin Homepage
Header
Top Slider
Footer
Signup
Manual Signup
Facebook
Google
Login
Manuall Login
Facebook
Google
Forgot & Reset Pwd
ForgorPassword Screen & Email
Reset Pwd screen
Logout
Sprint-2
Data Modeling
Rest of the modules
Admin Section
Users List
Add
Institution's List
Add
Project Page-Part1
Create & Edit Project
CC - Join Project Button
CC - Make Payment Button
Add to Wishlist
Refer to Friend
Contact Owner
Archive Option
CC - Related Documents
Key Points
Team Members List small and full view
Facebook Widget
Project Slider
Project Highlights, Fund raised, Materials, Services, Location
Project Brief
Sprint-3
Project Page-Part2
Project Wall
List of Attachments Popup
CC - Share on Social media (Project and Tasks sharing)
Facebook
Google Plus
Linked in
Prelogin Homepage
Display Data - Projects Statistics
Featured Projects
RecentlyProject
Completed Projects
Grid of Projects
View - Add - Edit
Mark projects for Display on Home
Mark projects for Successfully Completion & Display on Home
Sprint-4
Project Part-3
Project Progress Bar, Rating
Rating Summary
Rating Details
Hours/Things/Money etc. Statistics
Tasks Within project
List of Tasks
Active Tasks
Unassigned Tasks
Completed Tasks
Tasks Details
Tasks Summary
Related Photos & Documents
CC - Make Payment Button
CC - Join Tasks
Activity Log
Create & Edit Tasks
Create Task as per the Proto
Admin
Grid of Tasks
View - Add - Edit
Sprint-5
Admin Section
Users List
Edit - Delete
Block / Activate
Institution's List
Edit
Block / Activate
Delete users
CC - Donation Button
Donation option popup
Donation Form
Commision Calculation
Payment Process - Confirmation Page
User's OR Institution Profile Page
Personal Information
View
Add - Edit
Chanagee BG Photo
Change Profile Photo
Change Password Box
Contact Info View - Add - Edit - Delete
Keywords View - Add - Edit - Delete
Working Exp Add - Edit - Delete
Education Add - Edit- Delete
Volunteer Add - Edit - Delete
Bank A/c Add - Edit - Delete
Interest Add - Edit - Delete
Skills Add- Edit - Delete
Certificates Add- Edit - Delete
User's Mapping with Institution
Sprint-6
Admin
Project Category - Add/Edit/Delete
User Skills Category - Add/Edit/Delete
User's Activity Preferences
CC - Category selection List
Selection, Add, Remove and Save
CC- Search Category
TAB for Giver
TAB for Reciver
TAB for Moderator
User's Project
CC - Browse Project & Search
Tabs Assigned, Moderated, Wishlist,
Tab Settings
CC - Leave Project Button
CC - Refer to Friends Button
CC - Contact Owner Button
CC - Completed Projects Button
CC - Ongoing Projects Button
CC - Menu Control
Sprint-7
BrowsProject
CC - ProjectList-Engine with breif details
CC - Join Project Button
CC - Make Payment Button
Filter options
Sort option
CC - Search
Keyword Search
Options as People, Institute
ProfileView
View information
CC - Project Invite
CC - Connect
Institutional Menu (Rest all the options are same
CC - Institution List
List of User's institution
Sprint-8
Message Board
CC - List of Messages
Answer Button
ButtonView All
Button Delete
Button Mark as read
Button Delete Selected
Button View Email
Button New
CC - Search Message
Inbox
Sent
Create Message
To-multiple, subject, body, Attachment
Tab Inobx
Tab Sent
View Message Single & Full History
CC-Wall
List of Project Activities - TBD, Filter basd on User/Project
Sprint-9
Connections List
CC - Filter/Search User
CC - Friend List
CC - Send Message Button
CC - Project Invite / Resend Invite / Cancel Invite
CC - Remove Friend button
CC - Accept Invite / Decline Invite
Friend Tab
Send Request Tab
Received Request Tab
Find Connection
Invite Users on Email
Invite Users on Social Media
Facebook
Google Plus
LinkedIn
Friend's Suggestion by System itself (You may know them)
CC - Connect Button
Sprint-10
User Home Page (In addition to MainHomePage)
35 | CC - Notification
37 | CC - Message Notification
Profile Switching - Personal, Inst.
Notification Area
List of Notification
Filter criteria - e.g. User based or Project based
View
Accept
Ignore
Decline
Mark as read
Delete Selected
Sprint-11
CC - Payment Getway Integration
CC Avenue
Dashboard - Dynamic with Widget - State Persistance
Widget - MyProjects small list for Dashboard
Widget-Wall
Widget- MyConnection Small List For Dashboard
Widget- MSG List small for Dashboard
Widget- MyNotification Small List for Dashboard
Widget Engine
Admin Section
Users List
Message
Invite Users
Activity
Apoint Moderator
Modderator Request's Users List
Accept / Reject User's Moderator Request
Institution's List
Message
Invite Users
Activity
Apoint Moderator
Sprint-12
Payments Page
Payments Search
Payments Grid
Payments Details Popup
Payment Refund
Export to Excel, PDF
Notifications List
Notification Filter
Logs
Logs Filter
Tab - User based logs
Tab - Projects Logs
Tab - Payment Logs
Reports
5-7 Different Reports
Content Pages
MainPage-Banners, Add - Edit, Set Project Category
About us
FAQ
Contacts
Privacy Ppolicy